## Sprint 2
TEST PLAN (Original)
No | Product | Function | Detail | Action | Estimate time (hour) | Start date plan | Start date actual | Due date | Assignee | Status | Note
1 | Web | Settings - Contact | Contact List & Create & Edit & Delete | Design Test case | 2 | 2025-03-26 |  | 2025-03-26 | dung.nguyenthi@adamosoft.com | Done
2 |  |  |  | Review Test case | 0.5 | 2025-03-26 |  | 2025-03-26 | phuongnam.dangle@adamosoft.com | Done
3 |  |  | Contact List & Create & Edit & Delete | Execute Test case | 3 | 2025-03-31 |  | 2025-03-31 | dung.nguyenthi@adamosoft.com | Done
6 |  | Settings - Tag | Tag List & Create & Edit & Delete | Design Test case | 2 | 2025-03-26 |  | 2025-03-26 | dung.nguyenthi@adamosoft.com | Done
7 |  |  |  | Review Test case | 0.5 | 2025-03-26 |  | 2025-03-26 | phuongnam.dangle@adamosoft.com | Done
8 |  |  | Tag List & Create & Edit & Delete | Execute Test case | 4 | 2025-03-31 |  | 2025-03-31 | dung.nguyenthi@adamosoft.com | Done
11 |  | Settings - Deal | Deal List & Create & Edit & Delete | Design Test case | 1 | 2025-03-26 |  | 2025-03-26 | dung.nguyenthi@adamosoft.com | Done
12 |  |  |  | Review Test case | 1 | 2025-03-26 |  | 2025-03-26 | phuongnam.dangle@adamosoft.com | Done
13 |  |  | Deal List & Create & Edit & Delete | Execute Test case | 4 | 2025-04-01 |  | 2025-04-01 | dung.nguyenthi@adamosoft.com | Done
16 |  | Contacts - List view Filter | List & Sort & Edit | Design Test case | 2025-05-01 | 2025-03-27 |  | 2025-03-27 | dung.nguyenthi@adamosoft.com | Done
17 |  |  | Create | Design Test case | 1 | 2025-03-27 |  | 2025-03-27 | dung.nguyenthi@adamosoft.com | Done
18 |  |  | Delete | Design Test case | 1 | 2025-03-27 |  | 2025-03-27 | dung.nguyenthi@adamosoft.com | Done
19 |  |  |  | Review test case | 0.5 | 2025-03-27 |  | 2025-03-27 | phuongnam.dangle@adamosoft.com | Done
20 |  |  | List & Sort & Edit | Execute Test case | 2025-05-01 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
21 |  |  | Create | Execute Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
22 |  |  | Delete | Execute Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
27 |  | Contacts - Contact List | Edit information | Design Test case | 1 | 2025-03-27 |  | 2025-03-27 | dung.nguyenthi@adamosoft.com | Done
30 |  |  |  | Review test case | 0.5 | 2025-03-27 |  | 2025-03-27 | phuongnam.dangle@adamosoft.com | Done
31 |  |  | Edit information | Execute Test case | 1 | 2025-04-01 |  | 2025-04-01 | dung.nguyenthi@adamosoft.com | Done
34 |  | Contacts - Contact Detail | View contact detail | Design Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
36 |  |  | Overview | Design Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
37 |  |  | Update all information | Design Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
38 |  |  |  | Review Test case | 0.5 | 2025-03-28 |  | 2025-03-28 | phuongnam.dangle@adamosoft.com | Done
39 |  |  | View contact detail | Execute Test case | 1 | 2025-04-02 |  | 2025-04-02 | dung.nguyenthi@adamosoft.com | Done
41 |  |  | Overview | Execute Test case | 1 | 2025-04-02 |  | 2025-04-02 | dung.nguyenthi@adamosoft.com | Done
42 |  |  | Update all information | Execute Test case | 1 | 2025-04-02 |  | 2025-04-02 | dung.nguyenthi@adamosoft.com | Done
43 |  | Contacts Detail - Activity - Notes | View list of notes | Design Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
44 |  |  | Add new note | Design Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
45 |  |  | Edit note | Design Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
46 |  |  | Delete note | Design Test case | 1 | 2025-03-28 |  | 2025-03-28 | dung.nguyenthi@adamosoft.com | Done
47 |  |  |  | Review Test case | 0.5 | 2025-03-28 |  | 2025-03-28 | phuongnam.dangle@adamosoft.com | Done
48 |  |  | View list of notes | Execute Test case | 1 | 2025-04-02 |  | 2025-04-02 | dung.nguyenthi@adamosoft.com | Done
49 |  |  | Add new note | Execute Test case | 1 | 2025-04-02 |  | 2025-04-02 | dung.nguyenthi@adamosoft.com | Done
50 |  |  | Edit note | Execute Test case | 1 | 2025-04-02 |  | 2025-04-02 | dung.nguyenthi@adamosoft.com | Done
51 |  |  | Delete note | Execute Test case | 1 | 2025-04-02 |  | 2025-04-02 | dung.nguyenthi@adamosoft.com | Done
52 | Testing | Intergration Testing |  | Integrate testing | 1 | 2025-04-03 |  | 2025-04-03 | dung.nguyenthi@adamosoft.com | Done
53 | Testing | Bug Verification |  | Execute Test case | 1 | 2025-04-03 |  | 2025-04-03 | dung.nguyenthi@adamosoft.com | Done
54 | Testing | Regression Testing |  | Execute Test case | 1 | 2025-04-03 |  | 2025-04-03 | dung.nguyenthi@adamosoft.com | Done
TEST PLAN (Over scope)
No | Product | Function |  | Action | [5 empty] | Status | Note
1 | Web | Deals - Deals list | View & Search & Filter | Design Test case |  |  |  |  | dung.nguyenthi@adamosoft.com | Done
2 |  |  | Choose list view & Create | Design Test case |  |  |  |  | dung.nguyenthi@adamosoft.com | Done
3 |  |  |  | Review Test case |  |  |  |  | phuongnam.dangle@adamosoft.com | Done
4 |  |  | View & Search & Filter | Execute Test case |  |  |  |  | dung.nguyenthi@adamosoft.com | Done
5 |  |  | Choose list view & Create | Execute Test case |  |  |  |  | dung.nguyenthi@adamosoft.com | Done
6 |  | Deals - List view | List & Sort & Delete | Design Test case |  |  |  |  | dung.nguyenthi@adamosoft.com | Done
7 |  |  | Create & Edit | Design Test case |  |  |  |  | dung.nguyenthi@adamosoft.com | Done
8 |  |  |  | Review Test case |  |  |  |  | phuongnam.dangle@adamosoft.com | Done
9 |  |  | List & Sort & Delete | Execute Test case |  |  |  |  | dung.nguyenthi@adamosoft.com | Done
10 |  |  | Create & Edit | Execute Test case |  |  |  |  | dung.nguyenthi@adamosoft.com | Done

## Sprint 3
TEST PLAN (Original)
No | Product | Function | Detail | Action | Estimate time (hour) | Start date plan | Start date actual | Due date | Assignee | Status | Note
1 | Web | Contact detail - Task | View & Add | Design Test case | 2 | 2025-04-10 | 2025-04-10 |  | dung.nguyenthi@adamosoft.com | Done
2 |  |  |  | Review test case | 0.5 | 2025-04-10 | 2025-04-10 |  | phuongnam.dangle@adamosoft.com | Done
3 |  |  | View & Add | Execute Test case | 2 | 2025-04-16 | 2025-04-16 |  | dung.nguyenthi@adamosoft.com | Done
4 |  | Deals - Deals list | Change stage | Design Test case | 2 | 2025-04-11 | 2025-04-11 |  | dung.nguyenthi@adamosoft.com | Done
5 |  |  |  | Review Test case | 0.5 | 2025-04-11 | 2025-04-11 |  | phuongnam.dangle@adamosoft.com | Done
6 |  |  | Change stage | Execute Test case | 2 | 2025-04-16 | 2025-04-16 |  | dung.nguyenthi@adamosoft.com | Done
7 |  | Deals Detail - Overview | View Deal Detail | Design Test case | 2 | 2025-04-11 | 2025-04-11 |  | dung.nguyenthi@adamosoft.com | Done
8 |  |  |  | Review Test case | 0.5 | 2025-04-11 | 2025-04-11 |  | phuongnam.dangle@adamosoft.com | Done
9 |  |  | View Deal Detail | Execute Test case | 2 | 2025-04-16 | 2025-04-16 |  | dung.nguyenthi@adamosoft.com | Done
10 |  | Deals Detail - Task | View & Add | Design Test case | 2 | 2025-04-14 | 2025-04-14 |  | dung.nguyenthi@adamosoft.com | Done
11 |  |  |  | Review Test case | 0.5 | 2025-04-14 | 2025-04-14 |  | phuongnam.dangle@adamosoft.com | Done
12 |  |  | View & Add | Execute Test case | 2 | 2025-04-17 | 2025-04-17 |  | dung.nguyenthi@adamosoft.com | Done
13 |  | Deals Detail - Milestone | View list milestone | Design Test case | 2 | 2025-04-14 | 2025-04-14 |  | dung.nguyenthi@adamosoft.com | Done
14 |  |  |  | Review Test case | 0.5 | 2025-04-14 | 2025-04-14 |  | phuongnam.dangle@adamosoft.com | Done
15 |  |  | View list milestone | Execute Test case | 2 | 2025-04-17 | 2025-04-17 |  | dung.nguyenthi@adamosoft.com | Done
16 |  | Deals Detail - Note | View & Delete | Design Test case | 2 | 2025-04-14 | 2025-04-14 |  | dung.nguyenthi@adamosoft.com | Done
17 |  |  | Add & Edit | Design Test case | 2 | 2025-04-15 | 2025-04-15 |  | dung.nguyenthi@adamosoft.com | Done
18 |  |  |  | Review Test case | 0.5 | 2025-04-15 | 2025-04-15 |  | phuongnam.dangle@adamosoft.com | Done
19 |  |  | View & Delete | Execute Test case | 2 | 2025-04-17 | 2025-04-17 |  | dung.nguyenthi@adamosoft.com | Done
20 |  |  | Add & Edit | Execute Test case | 2 | 2025-04-18 | 2025-04-18 |  | dung.nguyenthi@adamosoft.com | Done
21 |  | Tasks - Task list | Task view & search & filter | Design Test case | 2 | 2025-04-15 | 2025-04-15 |  | dung.nguyenthi@adamosoft.com | Done
22 |  |  | Task add new & delete | Design Test case | 2 | 2025-04-15 | 2025-04-15 |  | dung.nguyenthi@adamosoft.com | Done
23 |  |  |  | Review test case | 0.5 | 2025-04-15 | 2025-04-15 |  | phuongnam.dangle@adamosoft.com | Done
24 |  |  | Task view & search & filter | Execute Test case | 2 | 2025-04-18 | 2025-04-18 |  | dung.nguyenthi@adamosoft.com | Done
25 |  |  | Task add new | Execute Test case | 2 | 2025-04-18 | 2025-04-18 |  | dung.nguyenthi@adamosoft.com | Done
TEST PLAN (Over scope)
No | Product | Function |  | Action | [5 empty] | Status | Note
New

## Sprint 4
TEST PLAN (Original)
No | Product | Function | Detail | Action | Estimate time (hour) | Start date plan | Start date actual | Due date | Assignee | Status | Note
1 | Web | Task list | Update | Design Test Case | 1.5 | 2025-04-23 | 2025-04-23 |  | dung.nguyenthi@adamosoft.com | Done
2 |  |  | Edit | Design Test Case | 1.5 | 2025-04-23 | 2025-04-23 |  | dung.nguyenthi@adamosoft.com | Done
3 |  |  |  | Review Test Case | 0.5 | 2025-04-23 | 2025-04-23 |  | dung.nguyenthi@adamosoft.com | Done
4 |  |  | View Detail | Execute Test Case | 1 | 2025-04-23 | 2025-04-23 |  | dung.nguyenthi@adamosoft.com | Done
5 |  |  | Filter | Execute Test Case | 1 | 2025-04-23 | 2025-04-23 |  | dung.nguyenthi@adamosoft.com | Done
6 |  |  | Edit | Execute Test Case | 1 | 2025-04-23 | 2025-04-23 |  | dung.nguyenthi@adamosoft.com | Done
7 |  |  | Update | Execute Test Case | 1 | 2025-04-23 | 2025-04-23 |  | dung.nguyenthi@adamosoft.com | Done
8 |  |  | Delete | Execute Test Case | 1 | 2025-04-23 | 2025-04-23 |  | dung.nguyenthi@adamosoft.com | Done
9 |  |  | Verify bugs | Verify bugs | 1 | 2025-04-24 | 2025-04-24 |  | dung.nguyenthi@adamosoft.com | Done
10 |  | Contact Exchange | Preview contact | Research SRS | 3 | 2025-04-23 | 2025-04-23 |  | my.nguyenviet@adamosoft.com | Done
11 |  |  | Preview contact | Research SRS | 2 | 2025-04-24 | 2025-04-24 |  | dung.nguyenthi@adamosoft.com | Done
12 |  |  | Releasing and Choosing contacts | Research SRS | 3 | 2025-04-23 | 2025-04-23 |  | my.nguyenviet@adamosoft.com | Done
13 |  |  | Releasing and Choosing contacts | Research SRS | 3 | 2025-04-24 | 2025-04-24 |  | dung.nguyenthi@adamosoft.com | Done
14 |  |  | Notification | Research SRS | 3 | 2025-04-24 | 2025-04-24 |  | my.nguyenviet@adamosoft.com | Done
15 |  |  | Notification | Research SRS | 2 | 2025-04-25 | 2025-04-25 |  | dung.nguyenthi@adamosoft.com | Done
16 |  |  | Preview contact | Design Test Case | 3 | 2025-04-25 | 2025-04-25 |  | dung.nguyenthi@adamosoft.com | Done
17 |  |  | Releasing contacts | Design Test Case | 3 | 2025-04-23 | 2025-04-23 |  | my.nguyenviet@adamosoft.com | Done
18 |  |  | Choosing contact | Design Test Case | 2 | 2025-04-25 | 2025-04-25 |  | my.nguyenviet@adamosoft.com | Done
19 |  |  | Notification | Design Test Case | 3 | 2025-04-24 | 2025-04-24 |  | my.nguyenviet@adamosoft.com | Done
20 |  |  | Notification | Review Test Case | 2 | 2025-04-25 | 2025-04-25 |  | dung.nguyenthi@adamosoft.com | Done
21 |  |  | Preview contact | Execute Test Case | 2 | 2025-04-29 | 2025-04-29 |  | dung.nguyenthi@adamosoft.com | Done
22 |  |  | Choose contact | Execute Test Case | 3 | 2025-04-28 |  |  | my.nguyenviet@adamosoft.com | Done
23 |  |  | Notification | Execute Test Case | 2 | 2025-04-26 |  |  | my.nguyenviet@adamosoft.com | New
24 |  | Contacts | Dupplicate Contact | Research SRS | 2 | 2025-04-26 | 2025-04-26 |  | dung.nguyenthi@adamosoft.com | Done
25 |  |  | Dupplicate Contact | Research SRS | 2 | 2025-04-28 | 2025-04-28 |  | my.nguyenviet@adamosoft.com | Done
26 |  |  | Dupplicate Contact | Design Test Case | 3 | 2025-04-26 | 2025-04-26 |  | dung.nguyenthi@adamosoft.com | Done
27 |  |  | Dupplicate Contact | Review Test Case | 1 | 2025-04-29 | 2025-04-29 |  | my.nguyenviet@adamosoft.com | Done
28 |  |  | Dupplicate Contact | Execute Test Case | 3 | 2025-04-29 | 2025-04-29 |  | dung.nguyenthi@adamosoft.com | Done
33 |  |  | List view & Filters | Verify bugs | 2 | 2025-04-28 | 2025-04-29 |  | dung.nguyenthi@adamosoft.com | Done
34 |  | Deal | Change stage of deal | Verify bugs | 2 | 2025-04-28 | 2025-04-28 |  | dung.nguyenthi@adamosoft.com | Done
35 |  |  | Update all infor of deal | Execute Testcase | 3 | 2025-04-28 | 2025-04-29 |  | dung.nguyenthi@adamosoft.com | Done
TEST PLAN (Over scope)
No | Product | Function |  | Action | [5 empty] | Status | Note
New

## Sprint 5
TEST PLAN (Original)
No | Product | Function | Detail | Action | Estimate time (hour) | Start date plan | Start date actual | Due date | Assignee | Status | Note
1 | Web | CR (Change Requiment) | Change lifecycle stage of contact | Design Test Case | 2 | 2025-05-06 | 2025-05-06 |  | dung.nguyenthi@adamosoft.com | Done
2 |  |  |  | Review Test Case | 1 | 2025-05-07 |  |  | my.nguyenviet@adamosoft.com | Done
3 |  |  | Renew deal | Design Test Case | 2 | 2025-05-06 |  |  | my.nguyenviet@adamosoft.com | Done
4 |  |  | change contact stage as deal changed | Design Test Case | 2 | 2025-05-06 | 2025-05-06 |  | my.nguyenviet@adamosoft.com | Done
5 |  |  |  | Review Test Case | 1 | 2025-05-07 |  |  | dung.nguyenthi@adamosoft.com | Done
6 |  |  | Change lifecycle stage of contact | Execute Test Case | 3 | 2025-05-08 | 2025-05-08 |  | dung.nguyenthi@adamosoft.com | Done
7 |  |  | Renew deal | Execute Test Case | 3 |  |  |  | my.nguyenviet@adamosoft.com | Done
8 |  |  | change contact stage as deal changed | Execute Test Case | 3 |  |  |  | my.nguyenviet@adamosoft.com | Pending
9 |  | Integration test | Deal - Contact | Execute Test Case | 3 | 2025-05-06 |  |  | my.nguyenviet@adamosoft.com | Done
10 |  |  | Staff - Contact | Execute Test Case | 3 | 2025-05-06 | 2025-05-06 |  | dung.nguyenthi@adamosoft.com | Done
11 |  |  | Deal - KPI | Execute Test Case | 3 |  |  |  | my.nguyenviet@adamosoft.com | Done
12 |  |  | Task - Contact | Execute Test Case | 3 | 2025-05-06 | 2025-05-06 |  | dung.nguyenthi@adamosoft.com | Done
13 |  |  | Noti & Contact | Execute Test Case | 3 |  |  |  | dung.nguyenthi@adamosoft.com | Done
14 |  |  | Noti & Contact | Execute Test Case | 3 | 2025-05-08 |  |  | my.nguyenviet@adamosoft.com | Pending
15 |  | KPIs | KPI Calculation | Research SRS | 2 | 2025-05-07 | 2025-05-07 |  | dung.nguyenthi@adamosoft.com | Done
16 |  |  | KPI Calculation | Research SRS | 2 | 2025-05-07 |  |  | my.nguyenviet@adamosoft.com | Done
17 |  |  | Personal contact | Design Test Case | 2 | 2025-05-07 | 2025-05-07 |  | dung.nguyenthi@adamosoft.com | Done
18 |  |  | Company contact | Design Test Case | 3 | 2025-05-07 | 2025-05-07 |  | dung.nguyenthi@adamosoft.com | Done
19 |  |  | Existing Customer | Design Test Case | 3 | 2025-05-08 | 2025-05-07 |  | dung.nguyenthi@adamosoft.com | Done
20 |  |  |  | Review Test Case | 1 | 2025-05-08 |  |  | my.nguyenviet@adamosoft.com | Done
21 |  |  | Delete deal | Design Test Case | 4 | 2025-05-07 |  |  | my.nguyenviet@adamosoft.com | New
22 |  |  | Lose deal | Design Test Case | 4 | 2025-05-08 |  |  | my.nguyenviet@adamosoft.com | New
23 |  |  |  | Review Test Case | 1 | 2025-05-08 | 2025-05-08 |  | dung.nguyenthi@adamosoft.com | Done
24 |  |  | Personal contact | Execute Test Case | 4 |  |  |  | dung.nguyenthi@adamosoft.com | Done
25 |  |  | Company contact | Execute Test Case | 4 |  |  |  | dung.nguyenthi@adamosoft.com | Done
26 |  |  | Existing Customer | Execute Test Case | 4 |  |  |  | dung.nguyenthi@adamosoft.com | Done
27 |  |  | Delete deal | Execute Test Case | 4 |  |  |  | my.nguyenviet@adamosoft.com | New
28 |  |  | Lose deal | Execute Test Case | 4 |  |  |  | my.nguyenviet@adamosoft.com | New
29 |  | Verify bug |  | Verify bugs | 2 | 2025-05-05 | 2025-05-05 |  | dung.nguyenthi@adamosoft.com | Done
30 |  |  |  | Verify bugs | 2 | 2025-05-05 | 2025-05-05 |  | my.nguyenviet@adamosoft.com | Done
81

## Sprint 6
TEST PLAN (Original)
No | Product | Function | Detail | Action | Estimate time (hour) | Start date plan | Start date actual | Due date | Assignee | Status | Note
1 | Web | KPIs | KPI for admin | Research SRS | 2 | 2025-05-19 | 2025-05-19 |  | my.nguyenviet@adamosoft.com | Done
2 |  |  | KPI for admin | Research SRS | 2 | 2025-05-19 | 2025-05-19 |  | dung.nguyenthi@adamosoft.com | Done
3 |  |  | KPI list | Design Test Case | 3 | 2025-05-19 | 2025-05-19 |  | dung.nguyenthi@adamosoft.com | Done
4 |  |  | Configure KPI | Design Test Case | 3 | 2025-05-20 | 2025-05-20 |  | dung.nguyenthi@adamosoft.com | Done
5 |  |  | Update KPI | Design Test Case | 3 | 2025-05-20 | 2025-05-20 |  | dung.nguyenthi@adamosoft.com | Done
6 |  |  |  | Review Test Case | 2 | 2025-05-21 | 2025-05-21 |  | my.nguyenviet@adamosoft.com | Done
7 |  |  | KPI list | Execute Test Case | 3 | 2025-05-26 | 2025-05-26 |  | dung.nguyenthi@adamosoft.com | Done
8 |  |  | Configure KPI | Execute Test Case | 3 | 2025-05-26 | 2025-05-26 |  | dung.nguyenthi@adamosoft.com | Done
9 |  |  | Update KPI | Execute Test Case | 3 | 2025-05-27 | 2025-05-27 |  | dung.nguyenthi@adamosoft.com | Done
10 |  |  | KPI calculation - Delete deal | Execute Test Case | 3 |  |  |  |  | Done
11 |  |  | KPI calculation - Lose deal | Execute Test Case | 3 | 2025-05-27 | 2025-05-27 |  | my.nguyenviet@adamosoft.com | Done
12 |  | Contact | Import | Design Test Case | 2 | 2025-05-20 | 2025-05-20 |  | my.nguyenviet@adamosoft.com | Done
13 |  |  | Export | Design Test Case | 2 | 2025-05-20 | 2025-05-20 |  | my.nguyenviet@adamosoft.com | Done
14 |  |  |  | Review Test Case | 2 | 2025-05-28 | 2025-05-28 |  | dung.nguyenthi@adamosoft.com | Done
15 |  |  | Import | Execute Test Case | 3 | 2025-05-28 | 2025-05-28 |  | dung.nguyenthi@adamosoft.com | Done
16 |  |  | Export | Execute Test Case | 3 | 2025-05-28 | 2025-05-28 |  | dung.nguyenthi@adamosoft.com | Done
17 |  | Role permission | Contacts | Design Test Case | 2 | 2025-05-21 | 2025-05-21 |  | dung.nguyenthi@adamosoft.com | Done
18 |  |  | Deal | Design Test Case | 2 | 2025-05-21 | 2025-05-21 |  | dung.nguyenthi@adamosoft.com | Done
19 |  |  | Task | Design Test Case | 2 | 2025-05-21 | 2025-05-21 |  | dung.nguyenthi@adamosoft.com | Done
20 |  |  |  | Review Test Case | 2 | 2025-05-22 | 2025-05-22 |  | my.nguyenviet@adamosoft.com | Done
21 |  |  | Contacts | Execute Test Case | 3 | 2025-05-27 | 2025-05-27 |  | dung.nguyenthi@adamosoft.com | Done
22 |  |  | Deal | Execute Test Case | 3 |  |  |  |  | Done
23 |  |  | Task | Execute Test Case | 3 |  |  |  |  | Done
24 |  |  | Staff | Design Test Case | 3 | 2025-05-22 | 2025-05-22 |  | dung.nguyenthi@adamosoft.com | Done
25 |  |  | KPIs | Design Test Case | 3 | 2025-05-22 | 2025-05-22 |  | dung.nguyenthi@adamosoft.com | Done
26 |  |  | Setting | Design Test Case | 3 | 2025-05-26 | 2025-05-26 |  | dung.nguyenthi@adamosoft.com | Done
27 |  |  |  | Review Test Case | 2 | 2025-05-28 | 2025-05-28 |  | my.nguyenviet@adamosoft.com | Done
28 |  |  | Staff | Execute Test Case | 3 | 2025-05-29 | 2025-05-29 |  | dung.nguyenthi@adamosoft.com | Done
29 |  |  | KPIs | Execute Test Case | 3 | 2025-05-29 | 2025-05-29 |  | dung.nguyenthi@adamosoft.com | Done
30 |  |  | Setting | Execute Test Case | 3 | 2025-05-29 | 2025-05-29 |  | dung.nguyenthi@adamosoft.com | Done
31 |  | Web | Stage Env | Verify bugs | 2 | 2025-05-21 | 2025-05-21 |  | my.nguyenviet@adamosoft.com | Done
32 |  |  | Stage Env | Verify bugs | 2 | 2025-05-21 | 2025-05-21 |  | dung.nguyenthi@adamosoft.com | Done
33 |  |  | Dev Env | Verify bugs | 2 | 2025-05-22 | 2025-05-22 |  | my.nguyenviet@adamosoft.com | Done
34 |  |  | Dev Env | Verify bugs | 2 | 2025-05-22 | 2025-05-22 |  | dung.nguyenthi@adamosoft.com | Done
35 |  | Web | Stage Env | Smoke test | 3 | 2025-05-29 | 2025-05-29 |  |  | Done
36 |  |  | Stage Env | Smoke test | 3 |  |  |  |  | Done
37 |  |  | Dev Env | Smoke test | 3 |  |  |  |  | Done
38 |  |  | Dev Env | Smoke test | 3 |  |  |  |  | Done
99

## Scope module tổng
Module | Sub | Detail | Status | Note
Authentication | Login
Logout
Dashboard
Contact | Show all contact | Show detail a contact
Search/Filter/Sort
Add new
|  | Edit |  | Phân quyền
Delete
Import
Export
| Contact exchange | Show list
Preview contact
|  | Choose contact |  | Hiểu là following contact này khi chưa có ai follow
|  | Show notification |  | List behavior liên quan đến notification
| Custom filter | Add new filter and save
Deal | Add new
Search/Filter
Update status by drag/drop
Show detail
Delete
Renew
Restore
Export
| Custom filter | Add new filter and save
Task | Show list
Search/Filter
Add new
Edit info
Delete
Update task
Staff | Staff list | Show list
Search/Filter
Add new
Edit
Delete
| Teams | Show list
Search
Add new
Edit
Delete
KPI | Show list
Search/Filter/Sort
Configure KPI for member
Approve KPI
Edit
Settings | Deals | Show list
Edit stage
| Industries | Show list
Add new
Edit
Delete
| Tag | Show list
Add new
Edit
Delete